# AQP ethics amendment summary

Version: 1.0 — 9 August 2026
Project: Accessible Questionnaire Platform (AQP)
Student researcher: Yurui Wang
Supervisor and study contact: Dr Mark Colley, m.colley@ucl.ac.uk
Existing approval ID: copy from the current approval letter before submission

## Decision requested

Approve one additional, observed formative usability study with 6–8 adult novice questionnaire researchers. This amendment does not request approval for the withdrawn respondent comparison with screen-reader or voice-input users.

No recruitment, consent or session will begin until written amendment approval is received. Submit this amendment by 11 August 2026. If approval is not in hand by 18 August 2026, no session data will enter the 21 August dissertation draft and the draft will not be delayed.

## Why the change is needed

The earlier self-administered researcher task relied on unobserved self-report. It could not reliably measure task success, time, assistance or errors. The revised study uses observable task outcomes, a fixed script and a pre-specified analysis plan. The dissertation remains complete without this study: quantified technical evaluation and a manual assistive-technology audit form the core evaluation. Approved sessions, if completed in time, are additional formative evidence only. Otherwise the fully specified protocol is reported as planned work and the researcher-usability claim remains not evidenced.

## Participants

- 6–8 adults aged 18 or over.

- Able to use a desktop or laptop browser and understand the study language.

- No prior development work on AQP.

- Novice or occasional questionnaire researchers: no more than two previously configured online questionnaire studies.

- Willing to take part in an observed remote session and consent to recording of the study window and session audio.

No diagnosis, health information or special-category personal data is requested. Routine experience with Qualtrics or another survey platform is recorded because it is a relevant task characteristic.

## What changes in the method

Each session lasts up to 75 minutes and uses synthetic questionnaire data only. Participants complete the same SUS setup task in two whole-tool conditions:

- AQP, starting from the researcher landing page with built-in SUS available.

- UCL Qualtrics, starting from a fresh copy of the frozen AQP-SUS-COMPARISON-v1 template. The template already contains the ten SUS items, required settings, one-question-per-page presentation and verified Brooke score calculation.

The required end state is frozen in the protocol. Condition order is counterbalanced. The observer uses a fixed neutral script and does not coach. The study records task success, active time, assists, observable errors, the Single Ease Question, SUS for each system and three short open questions.

After both conditions, participants check a source sheet against an imported definition containing one mild, intentionally planted label difference. The information sheet tells participants that one task may contain a small intentional difference but does not reveal its location. The observer explains the exact difference immediately after the task and confirms that it was not the participant's mistake.

## Recording and incidental identifying material

With separate active consent, the study window and session audio are recorded only to code task time, assists and errors. A recording made on a participant's own computer may accidentally capture identifying material such as an account name, browser tabs, notifications, file paths or voice. Before recording, the participant is asked to close unrelated windows and mute notifications. They may pause or stop recording at any time, but the risk cannot be eliminated entirely.

The study does not intentionally record the participant's camera. The participant is asked not to open real participant data or unrelated private material during the session.

## Data handling, access and destruction

- Assign a study code. Keep contact and consent records separate from task data.

- Transfer each recording immediately to an access-controlled UCL Research Data Storage Service (RDSS) project folder registered by the supervisor. Verify the transfer, then securely remove the temporary local copy.

- Do not email recordings or upload them to GitHub, personal cloud storage or an open repository.

- Limit access to Yurui Wang, Dr Mark Colley and one named UCL second coder listed in the approved amendment. The second coder independently codes at least two sessions and receives only the minimum files needed.

- Delete raw screen/audio recordings no later than 30 November 2026, after primary coding and the pre-specified agreement check are complete. Record the deletion date.

- Retain consent records separately for the period required by the UCL Records Retention Schedule. Retain only de-identified coded research data for the approved research-retention period.

- A participant may request removal of their identifiable and coded data using their study code until seven calendar days after their session. After irreversible anonymisation and aggregation, individual removal may no longer be possible.

## Analysis and safeguards

Report per-participant data and descriptive summaries only: counts and denominators, median, minimum and maximum. Do not use significance tests or claim population effects at n=6–8. Define task success, assist and error before the first session. Preregister the protocol, frozen systems, counterbalancing, analysis and second-coder rule. A second person independently codes at least two recordings and pre-consensus agreement is reported.

The participant may take a break or stop without penalty. No payment is planned under this amendment. Adding payment, changing the recording route, recruiting a different participant group or adding a disabled-respondent study requires prior ethics confirmation and updated participant materials.

## Documents submitted with the amendment

- Observed Researcher Study Protocol v1.0.

- Participant Information Sheet v1.0.

- Consent Form v1.0.

- Project Risk Assessment v1.0.

- GDPR-compliant subject receipt form v1.0, marked not in use because no payment is planned.

## Submission gate

Before sending the amendment, enter the existing ethics approval ID and the name and UCL role of the independent second coder. Confirm that the supervisor has an active RDSS project folder for the recordings. No other bracketed study fields remain in the participant-facing documents.